## Implementer Table
[16 empty] | new columns |  |  |  | Apr 2026 is next quarterly update
EE Program Third-Party Implementers Table as of April 1, 2026 | [16 empty] | as of 04/01/26 (updated quarterly)
This tracker will include all contracts regardless of whether an Advice Letter was required. Refer to CEDARS for additional Program details. | [16 empty] | Program Closures and Program Extensions
IOU | Program Name | Solicitation Name | Program ID | Segment (MS/E/RA/Codes & Standards) | Primary Sector (Market Segment) | Sector (Sub‐segment / Type of Customers) | Delivery Channel | Vendor | Size of Customer | Contract Effective Date | Contract Length (In months) | Anticipated Program Launch Date (Open for enrollment) | Total Targeted Savings (kWh, MW, Therms) | Total Budget (In $) | Advice Letter | Original Contract End Date | Early Contract End Date (if applicable) | Updated Contract Duration (in months - cumulative) | Updated Contract End Date (based on updated duration) | Implementation Plan updated to reflect contract change (Y, N, or N/A) and date of IP update | Advice Letter
SCE | Willdan’s Comprehensive Commercial Program | Local Residential, Commercial and Industrial | SCE_3P_2020RCI_005 | Resource Acquisition | Commercial | All Customers in Sector that have a monthly maximum demand of greater than 20 kW | Downstream | Willdan Energy Solutions | Monthly maximum demand of greater than 20 kW | 2020-09-30 | 73 months | 2021-08-01 | 887,050,793 kWh 80 MW 8,635,183 Therms | 387600000 | Advice Letter 4348 | 2025-12-31 |  |  |  |  | Advice 5367-E
SCE | Willdan’s Comprehensive Industrial Program | Local Residential, Commercial and Industrial | SCE_3P_2020RCI_006 | Resource Acquisition | Industrial | All Customers in Sector that have a monthly maximum demand of greater than 20 kW | Downstream | Willdan Energy Solutions | Monthly maximum demand of greater than 20 kW | 2020-09-29 | 73 months | 2021-08-01 | 382,031,410 kWh 36 MW 5,190,482 Therms | 155000000 | Advice Letter 4349 | 2025-12-31 | 2024-02-29 | N/A | N/A | N/A | Advice 5281-E
SCE | Willdan’s Comprehensive Multifamily Program | Local Residential, Commercial and Industrial | SCE_3P_2020RCI_004 | Resource Acquisition | Residential | All | Downstream | Willdan Energy Solutions | All | 2020-09-29 | 72 months | 2021-07-01 | 150,628,504 kWh 17 MW 755,834 Therms | 82170000 | Advice Letter 4350 | 2025-12-31 | 2024-02-23 | N/A | N/A | N/A | Advice 5281-E
SCE | ICF Residential Behavioral Program | Local Residential, Commercial and Industrial | SCE_3P_2020RCI_002 | Resource Acquisition | Residential | All | Behavioral | ICF Resources LLC | All | 2020-09-30 | 52 months | 2022-01-01 | 416,376,491 kWh 140 MW 0 Therms | 38122591 | Advice Letter 4353 | 2025-12-31 | 2022-10-13 | N/A | N/A | N/A | Advice Letter 4969
SCE | ICF Commercial Behavioral Program | Local Residential, Commercial and Industrial | SCE_3P_2020RCI_003 | Resource Acquisition | Commercial | All customers in Sector with demand less than 250 kW | Behavioral | ICF Resources LLC | Monthly demand less than 250 kW | 2020-09-30 | 60 months | 2023-03-01 | 49,646,184 kWh 25 MW 0 Therms | 6530297 | Advice Letter 4354 | 2025-12-31 |  | 87 | 2027-12-31 | In progress
SCE | Enervee Marketplace | Local Residential, Commercial and Industrial | SCE_3P_2020RCI_001 | Resource Acquisition | Residential | All | Downstream | Enervee Corporation | All | 2020-09-30 | 52 months | 2022-05-01 | 36,802,057 kWh 10 MW 298,413 Therms | 19006236 | Advice Letter 4355 | 2025-12-31
SCE | CA Statewide Lighting Program | Statewide Lighting | SCE_SW_UL | Resource Acquisition | Commercial Industrial | All | Upstream Midstream | TRC Solutions, Inc. | All | 2020-09-30 | 45 months | 2021-07-01 | 63,472,500 kWh 9 MW 0 Therms | 36000000 | Advice Letter 4356 | 2024-10-01 | 2023-06-30 | N/A | N/A | N/A | N/A - D.23-06-055 provided CPUC approval for this program closure​
SCE | Statewide Electric Emerging Technologies Program (SWEETP) | Statewide Electric Emerging Technologies | SCE_SW_ETP_Elec | Resource Acquisition | All | All | N/A | Cohen Ventures, DBA Energy Solutions | All | 2021-09-14 | 76 months | 2021-09-01 | 0 kWh 0 MW 0 Therms | 67553849 | Advice Letter 4607 | 2027-12-31
SCE | Public Energy Performance (PEP) | Local Public | SCE_3P_2021AGPUB_002 | Resource Acquisition | Public | All | Downstream | CLEAResult Consulting Inc. | All | 2021-12-15 | 49 months | 2022-04-01 | 71,911,083 kWh 5 MW 0 Therms | 22762103 | Advice Letter 4724 | 2025-12-31 |  | 61 | 2026-12-31 | Y 2/20/2025 | Advice 5376-E
SCE | Agriculture Energy Efficiency Program (AgEE) | Local Agriculture | SCE_3P_2021AGPUB_001 | Resource Acquisition | Agricultural | All | Downstream | ICF Resources LLC | All | 2021-12-15 | 49 months | 2022-09-30 | 25,550,140 kWh 5 MW 0 Therms | 11499813 | Advice Letter 4740 | 2025-12-31 |  | 73 | 2027-12-31 | In progress | N/A
SCE | Higher Education Energy Performance | Statewide Higher Education | SCE_SW_IP_Colleges | Resource Acquisition | Public | Higher Education | Downstream | CLEAResult Consulting Inc. | All | 2022-02-09 | 46 months | 2022-10-01 | 28,904,420 kWh 2.1 MW 561,112 Therms | 12571286 | Advice Letter 4772 | 2025-12-31 |  | 59 | 2026-12-31 | Y 11/9/2024 | Advice 5311-E
SCE | Statewide Water Infrastructure & System Efficiency (SW WISETM) | Statewide Water/Wastewater Pumping | SCE_SW_WP | Resource Acquisition | Public | Water/Wastewater Pumping | Downstream | Lincus, Inc. | All | 2022-04-28 | 45 months | 2022-09-01 | 23,400,950 kWh 2,316 MW 216,347 Therms | 15481218 | Advice Letter 4816 | 2025-12-31 |  | 61 | 2027-05-31 | Y 5/28/2025
SCE | Disadvantaged Communities Marketing and Outreach Program | Local Residential Equity | SCE_Res_Equity_003 | Equity | Residential | All | N/A | Global Energy Services | All | 2023-03-31 | 33 Months | 2023-08-01 | N/A | 4275000 | N/A | 2025-12-31 |  |  |  |  | N/A
SCE | Residential Energy Advisor | Local Residential Equity | SCE_Res_Equity_001 | Equity | Residential | All | Downstream | CLEAResult Consulting Inc. | All | 2023-03-31 | 36 months | 2023-11-01 | 1,912,295 kWh 133 kW 26,710 Therms | 8381555.83 | Advice Letter 5030 | 2025-12-31 |  | 46 | 2026-12-31 | In Progress | N/A
SCE | Residential Energy Advisor | Local Residential Equity | SCE_Res_Equity_002 | Equity | Residential | All | N/A | CLEAResult Consulting Inc. | All | 2023-03-31 | 36 months | 2023-11-01 | N/A | 3896028 | Advice Letter 5030 | 2025-12-31 |  | 46 | 2026-12-31 | In Progress | N/A
SCE | Simplified Savings Program | Local Small/Medium Business Equity | SCE_SMB_Equity_001 | Equity | Agriculture, Commercial, Industrial, Public | Small/Medium Business | Downstream | Resource Innovations | Monthly demand less than 200 kW | 2023-05-22 | 41 months | 2023-12-01 | 4,158,019 kWh 476 kW 133,163 Therms | 14551738.58 | Advice Letter 5072 | 2026-09-01 |  | 56 | 2027-12-31 | In Progress | N/A
SCE | Commercial Energy Manager | Local Commercial Strategic Energy Management Program | SCE_3P_SEM_001 | Resource Acquisition | Commercial | All | Customer Facing | CLEAResult Consulting Inc. | All | 2024-01-26 | 64 months | 2024-08-01 | 9,573,000 kWh 7,332,980 kW 656,640 Therms | 28861380 | Advice Letter 5247
SCE | Industrial and Agriculture Energy Management Program | Local Industrial & Agricultural Strategic Energy Management Program | SCE_3P_SEM_002 SCE_3P_SEM_002A | Resource Acquisition | Industrial, Agriculture | All | Customer Facing | CLEAResult Consulting Inc. | All | 2024-01-26 | 64 months | 2024-08-01 | 15,390,000 kWh 2,154 kW 1,890,000 Therms | 29949001 | Advice Letter 5247
SCE | EnergyIMPRESS (Commercial) | Local Commercial Strategic Energy Management Program | SCE_3P_SEM_003 | Resource Acquisition | Commercial | All | Customer Facing | Cascade Energy | All | 2024-01-31 | 64 months | 2024-08-01 | 8,639,837 kWh 1,147 kW 72,758 Therms | 10446411 | Advice Letter 5246
SCE | EnergyIMPRESS (Industrial and Agricultural) | Local Industrial & Agricultural Strategic Energy Management Program | SCE_3P_SEM_004 SCE_3P_SEM_004A | Resource Acquisition | Industrial, Agriculture | All | Customer Facing | Cascade Energy | All | 2024-01-31 | 64 months | 2024-08-01 | 15,243,986 kWh 1,996 kW 195,152 Therms | 25182302 | Advice Letter 5246
SCE | Multifamily Residential DIrect Install Program | Local Residential Multifamily | SCE_3P_MF_001 | Resource Acquisition | Residential | Multifamily | Downstream | Synergy | All | 2024-08-16 | 48 months | 2025-01-01 | 17,991,621 kWh 12,175 kW 169,880 Therms | 20000000 | Advice Letter 5377-E | 2028-12-31
SCE | Grid-Responsive Incentive Design Market Access Program (GRID) | Local Market Access Program (MAP) | SCE_3P_2025MAP_001 | Resource Acquisition | Commercial, Public, Residential | All | Downstream | The Mendota Group | All | 2024-11-22 | 48 months | 2025-04-01 | 25,016,684 kWh 6,497 kW 117,656 Therms | 19999997 | Advice Letter 5455-E | 2028-12-31
SCE | Market Access Program (MAP) | Local Market Access Program (MAP) | SCE_3P_2025MAP_002 | Resource Acquisition | Commercial, Public | All | Downstream | Alternative Energy Systems Consulting (AESC) | All | 2024-11-22 | 48 months | 2025-04-01 | 28,845,000 kWH 4,543 kW 308,748 Therms | 19998971 | Advice Letter 5455-E | 2028-12-31
SCE | Comprehensive Refrigeration Energy Savings and Training (CREST) Program | Local Comprehensive Commercial | SCE_3P_2025C_002 | Resource Acquisition | Commercial | All | Downstream | Cascade Energy | All | 2025-01-28 | 60 months | 2025-10-01 | 6,353,216 kWH 870 kW 140,270 Therms | 6511030 | Advice Letter 5485-E | 2029-12-31
SCE | Commercial Energy Reduction Initiative (CERI) Program | Local Comprehensive Commercial | SCE_3P_2025C_001 | Resource Acquisition | Commercial | All | Downstream | Resource Innovations | All | 2025-01-28 | 60 months | 2026-12-22 | 68,678,181 kWH 7,157 kW 169,689 Therms | 19991497 | Advice Letter 5485-E | 2029-12-31
SCE | Residential Energy Solutions Program | Local Residential | SCE_3P_2025R_002 | Resource Acquisition | Residential | All | Downstream | Synergy | All | 2025-01-28 | 39 months | 2025-10-01 | 23,475,739 kWH 17,732 kW 899,257 Therms | 33000000 | Advice Letter 5486-E | 2028-12-31
SCE | Customer Home Engagement for Energy Reduction Program | Local Residential | SCE_3P_2025R_001 | Resource Acquisition | Residential | Single Family, Multifamily | Behavioral | Oracle | All | 2025-01-28 | 42 months | Upon AL Approval | 426,427,300 kWH 94,800 kW 0 Therms | 22667464 | Advice Letter 5486-E | 2028-12-31
SCE | Refrigeration Efficiency and Leak Mitigation (REALM) | Local Comprehensive Commercial | SCE_3P_2025C_003 | Resource Acquisition | Commercial | All | Downstream | Redwood Energy Services, Inc. | All | 2025-05-20 | 31 months | 2026-01-01 | 3,420,000 kWH | 4999900 | N/A | 2027-12-31
SCE | Industrial Incentive Solutions | Local Industrial | SCE_3P_2025I_001 | Resource Acquisition | Industrial | All | Downstream | Cohen Ventures, DBA Energy Solutions | All | 2025-06-27 | 60 months | 2025-12-25 | 15,617,317 kWh 1,433 kW 177,700 therms | 13531012 | Advice Letter 5607-E | 2030-12-31
SoCalGas | Commercial Building Energy Solutions and Technologies C-BEST) | Small and Medium Commercial | SCG3887 & SCG3940 | Resource Acquisition | Commercial | Small and Medium Commercial Business | Downstream | ICF | ≤50,000 therms/ year | 2020-12-19 | 36 months | 2020-08-30 | 1,023,737 net therms | 20463253 | Advice Letter 5732 | 2023-12-18 |  | 84 | 2027-12-31
SoCalGas | Public Direct Install Program | Small and Medium Public | SCG3886 | Resource Acquisition | Public | Small and Medium | Downstream | Synergy | Local and Federal Government and K-12 Educational Facilities | 2020-12-05 | 36 months | 2020-08-28 | 2,294,712 net therms | 18500000 | Advice Letter 5724 | 2023-12-20 |  | 84 | 2027-12-31
SoCalGas | Multifamily Energy Alliance (MEA) | Residential Multi-Family | SCG3889 & SCG3936 | Equity | Residential | Multifamily | Downstream | ICF |  | 2021-05-02 | 36 months | 2020-09-25 | 716,375 net therms | 23999999 | Advice Letter 5729-B | 2024-05-02 |  | 87 | 2027-12-31
SoCalGas | Multi-Family Space and Water Heating Controls (MF SAWH) Program | Residential Multi-Family | SCG3888 | Resource Acquisition | Residential | Multifamily (building owners) | Downstream | EnergX |  | 2020-12-24 | 36 Months | 2020-12-23 | 297,601 Therms 1,511,160 kWh 1,262,898 kW reduction | 1338039 | NA | 2023-12-31 |  | TBD | TBD
SoCalGas (SW) | California Foodservice Instant Rebates Program | Point of Sale Food Service | SCG_SW_FS | Market Support | Commercial | Foodservice | Midstream | Energy Solutions |  | 2021-01-15 | 36 months | 2021-12-09 | 18,104,200 net kWh 5,552,532 net therms | 46826772 | Advice Letter 5739 | 2024-01-14 |  | TBD | TBD
SoCalGas (SW) | Statewide Midstream Water Heating Program | Midstream Water Heating | SCG_SW_MCWH | Resource Acquisition | Commercial | Commercial, Multifamily (water heating) | Midstream | DNV GL |  | 2021-03-04 | 36 months | 2020-12-04 | 8,337,737 net kWh 4,721,771 net therms | 45840873 | Advice Letter 5737 | 2024-03-18 |  | TBD | TBD
SoCalGas | Service RCx+ | Large Commercial | SCG3891 | Resource Acquisition | Commercial | Large Commercial | Downstream | Enovity, Inc. | >50,000 therms/year | 2020-12-23 | 48 months | 2020-12-23 | 1,073,250 Therms | 5693811 | Advice Letter 5790 | 2025-06-04 |  | 48 | 2027-12-31
SoCalGas | Large Commercial Program | Large Commercial | SCG3892 | Resource Acquisition | Commercial | Large Commercial | Downstream | Willdan | >50,000 therms/year | 2020-12-16 | 48 months | 2020-12-21 | 3,097,915Therms 13,575,162 kWh 1,613 kW reduction | 28202197 | Advice Letter 5790-A | 2024-12-31 |  | 84 | 2027-12-31
SoCalGas | Comprehensive Manufactured Home Program (CMHP) | Manufactured Housing | SCG3884 | Equity | Residential | Manufactured Homes | Downstream | Synergy |  | 2020-12-23 | 36 months | 2020-12-22 | 718,047 Therms 2,994,295 kWh 27 kW reduction 50,534,545 gallons saved | 12800000 | NA | 2023-12-31 |  | 84 | 2027-12-31
SoCalGas | Comprehensive Manufactured Home Program (CMHP) | Manufactured Housing | SCG3885 | Equity | Residential | Manufactured Homes | Downstream | Staples & Associates |  | 2021-12-22 | 36 months | 2020-12-21 | 426,574 Therms 2,954,497 kWh 1,186 kW reduction | 2700000 | NA | 2023-12-31 |  | 48 | 2027-12-31
SoCalGas | Agriculture Energy Efficiency Program | Agricultural Sector | SCG3890 | Resource Acquisition | Agricultural |  | Downstream | ICF |  | 2021-04-08 | 36 months | 2020-12-14 | 1,192,195 Therms | 22266979 | Advice Letter 5773 | 2024-04-08 |  | 84 | 2027-12-31
SoCalGas | Innovative Gas Emerging Technology (IGET) Program | Gas Emerging Technologies | SCG_SW_ETP_Gas | Resource Acquisition | ET | Statewide Cross-Cutting | NonResource | ICF |  | 2021-08-24 | 36 months | 2021-06-24 | N/A | 8880804 | Advice Letter 5846 | 2024-08-24 |  | 48 | 2027-12-31
SoCalGas | Performance-Based Next Gen HERs for All | Behavioral | SCG3824 | Resource Acquisition | Residential | Single Family, Multifamily | Behavioral | Bidgely |  | 2021-10-01 | 36 months | 2021-10-01 | 6,893,952 Therms | 2078883 | NA | 2024-10-01 |  | 74 | 2027-12-31
SoCalGas | Residential Behavioral Program: Dynamic Actionable Customer Feedback (DACF) | Behavioral | SCG3824 | Resource Acquisition | Residential | Single Family, Multifamily | Behavioral | Oracle |  | 2022-01-05 | 36 months | 2021-10-29 | 26,550,000 Therms | 9279600 | Advice Letter 5903 | 2025-01-05 |  | 83 | 2027-12-31
SoCalGas | Performance-Based Next Gen HERs for SMB Customers | Behavioral | SCG3898 | Resource Acquisition | Commercial | Commercial | Resource | Bidgely | small and medium sized business customers | 2022-12-23 | 36 months | 2023-04-01 | 1,143,804 therms | $1,672,125 | NA | 2025-12-23
SoCalGas | SCG Outreach | Outreach | SCG3901 | Equity | Outreach | DAC/ HTR | Non-Resource | Global Energy Services |  | 2024-05-22 | 36 months | 2022-04-01 | TBD | 4950000 | NA | 2025-05-02
SoCalGas | Large Public | Large Public Sector (Re-Bid) |  | Resource Acquisition | Public | Public | Non-Resource | Energy Infrastructure Partners |  | 2022-10-01 | 36 months |  | TBD | 4882770 | NA | 2025-10-31
SoCalGas | i2iSEM | Industrial Segment Solutions | SCG3945 | Resource Acquisition | Industrial | Industrial | Downstream | Cascade Energy Inc. | >250,000 therms | 2022-12-23 | 60 months | Upon AL Approval | 2,209,410 Therms | 6800000 | Advice Letter 6113-A | 2027-12-31
SoCalGas | ISTAR | Industrial Segment Solutions | SCG3942 | Resource Acquisition | Industrial | Food & Beverage manufacturing, | Downstream | Cascade Energy Inc. | All | 2023-01-01 | 60 months | Upon AL Approval | 1,952,998 Therms | 5500000 | Advice Letter 6113-A | 2027-12-31
SoCalGas | Industrial Energy Partners (IEP) | Industrial Segment Solutions | SCG3943 | Resource Acquisition | Industrial | All - excluding Refineries, Food and Beverage | Downstream | CLEAResult Consulting Inc. |  | 2023-01-01 | 60 months | Upon AL Approval | 12571496 Therms | 24629078 | Advice Letter 6113-A | 2027-12-31
SoCalGas | Refinery Gas Energy Efficiency Program | Industrial Segment Solutions | SCG3944 | Resource Acquisition | Industrial | Refineries | Downstream | Willdan Energy Solutions | All | 2022-12-23 | 60 months | Upon AL l | 12,243,110 Therms | 23000000 | Advice Letter 6113-A | 2027-12-31
SoCalGas | SoCalGas Marketplace powered by Enervee | Marketplace | SCG3829 | Market Support | Marketplace | Residential, Small business | Downstream | Enervee Corporation | <50k therms, annually | 2022-12-29 | 36 months | 2023-03-01 | TBD | 12657232 | Advice Letter 6107 | 2025-12-31
SoCalGas | Comprehensive Multifamily Incentive (CoMFI) Program | Residential Multi-Family Whole Building | SCG3705 &SCG3938 | Equity | Residential | Multi-Family | Downstream | Richard Heath & Associates, Inc. |  | 2022-12-28 | 36 months | Q2 2023 | 2009289 therms, 591,030 kWh, 44,280,240 gallons | 18000000 | Advice Letter 6114 | 2025-12-31
SoCalGas | HERS Training by CHEERS | HERS Rater Training | SCG3760 | Market Support | Commercial | Current Raters, Energy industry technicians, Building trade technicians, Customer intermediaries | Downstream | ConSol Home Energy Efficiency Rating Services, Inc. |  | 2022-12-30 | 36 months | Q2 2023 | TBD | 4007200 | N/A | 2025-12-31
SoCalGas | Retail Channel Support | Retail Partnering | SCG3830 | Market Support | Commercial | Commercial | Non-Resource | ICF Resources, L.L.C |  | 2022-12-27 | 36 months | 2023-04-01 | TBD | 5389110 | N/A | 2025-12-31 |  | 60 | 2027-12-31
SoCalGas | Business Energy Efficiency Surveys (BEES) | Non-Residential EE Advisor | SCG3909 | Equity | Commercial | Non-Residential | Downstream | Richard Heath & Associates, Inc. |  | 2022-12-23 | 36 months | Q2 2023 | TBD | 2315750 | N/A | 2025-12-31
SoCalGas | Commercial Strategic Energy Management (SEM) | Commercial Strategic Energy Management (SEM) | SCG3939 | Resource Acquisition | Commercial | Commercial | Downstream | CLEAResult Consulting Inc. | >150,000 therms/year | 2024-01-12 | 48 months | Q2 2024 | TBD | 8397740 | Advice Letter 6298-G | 2028-12-31 |  | 59
SoCalGas | PUB-K-12 Public Schools Program | K-12 Public Schools Program | SCG3956 | Resource Acquisition | Public | Public | Resource | Okapi Architecture, Inc. | L | 2023-12-31 | 24 | 2024-01-01 |  | 699422 |  | 2025-12-31
SoCalGas | COM - Brewery Energy Efficiency and Recovery | Commercial - Brewery Energy Efficiency and Recovery BEER | SCG3957 | Resource Acquisition | Commercial | Commercial | Downstream | Frontier Energy, Inc. | S/M | 2023-12-31 | 24 | 2024-01-01 |  | 699850 |  | 2025-12-31
SoCalGas | RES-TEG Wall Furnace Direct Install | TEG Wall Furnace Direct Install) - Williams Furnace Company | SCG3960 | Resource Acquisition | Residential | Single-Family | Downstream | Williams Furnace Company | S | 2023-12-31 | 24 | 2024-01-01 |  | 700000 |  | 2025-12-31
SoCalGas | COM-Pool Heating Energy Efficiency Program | Pool Heating Energy Efficiency Program | SCG3961 | Resource Acquisition | Commercial | Commercial | Downstream | CEGY | L | 2023-12-31 | 24 | 2024-01-01 |  | 698320 |  | 2025-12-31
SoCalGas | COM-Small and Medium Commercial EE Program | COM-Small and Medium Commercial EE Program | SCG3882 & SCG3937 | Resource Acquisition | Commercial | Small and Medium Commercial Business | Downstream | Franklin Energy Services, LLC | L | 2020-09-24 | 87 |  |  | 16871728 |  | 2027-12-31
SoCalGas | COM-Energy Efficiency and Rehabilitation Program | COM-Energy Efficiency and Rehabilitation Program | SCG3970 | Market Support | Commercial | Commercial | Downstream | Eco Enertainment, Inc. | S/M | 2025-02-07 | 24 | 2025-01-01 |  | 699900 |  | 2027-02-07
SoCalGas | COM-Sustainability Studies and Solutions | COM-Sustainability Studies and Solutions | SCG3969 | Market Support | Commercial | Commercial | Downstream | Cascade Energy, LLC | L | 2024-11-20 | 24 | 2025-01-01 |  | 698744 |  | 2026-12-31
SoCalGas | Market Access Program | Market Access Program | TBD | Resource Acquisition | Commercial | Residential and Commercial | Downstream | Mendota Group, LLC. | S/M | 2025-06-06 | 36 | 2025-01-01 |  | 6994036 |  | 2027-12-31
SDG&E | The Small Commercial Program (SCP) | Small Commercial | SDGE4003 | Resource Acquisition | Commercial | Small Commercial | Downstream | Willdan Energy Solutions | Demand below 20 kW | 2020-06-30 | 45 months | 2021-01-01 | 83,548,627 kWh 14.4 MW 845,692 Therms | 46200000 | Advice Letter 3585 | 2024-03-31 | 2022-06-30 | 18 months | 2022-06-30 | Y - 12/9/2022 | Advice Letter 3972
SDG&E | Comprehensive Energy Management Solutions (CEMS) | Large Commercial | SDGE4004 | Resource Acquisition | Commercial | Large Commercial | Downstream | TRC Solutions | Demand above 20 kW | 2020-06-30 | 66 months | 2021-01-01 | 58,516,131 kWh 7.6 MW 2,272,197 Therms | 45680000 | Advice Letter 3584 | 2025-12-31 |  |  |  | N/A | Advice Letter 4513
SDG&E | Residential Zero Net Energy Transformation (RZNET) | Multi-Family | SDGE4002 | Resource Acquisition | Residential | Multi-Family | Downstream | Synergy Companies | All | 2020-06-30 | 42 months | 2021-01-01 | 2,709,073 kWh 856 kW 665,901 Therms | 14570000 | Advice Letter 3586 | 2023-12-31 |  | 69 months | 2026-03-31 | N
SDG&E | Comfortably California Program | Statewide Commercial/Residential HVAC | SDGE_SW_HVAC_Up_Com: SW HVAC Upstream Commercial SDGE_SW_HVAC_Up_Res: SW HVAC Upstream Residential | Resource Acquisition | Commercial and Residential | Statewide Upstream and Midstream HVAC Program | Midstream/Upstream | CLEAResult Consulting Inc. | All | 2020-10-14 | 39 months | 2021-01-01 | 60,235,134 kWh 19.7 MW 1,728,244 Therms | 36974313 | Advice Letter 3648 | 2023-12-31 |  | 71 months | 2026-12-31 | N
SDG&E | Federal Energy Program (FEP) | Public Sector-Federal | SDGE4012 | Resource Acquisition | Public | Federal- includes Federal Buildings, US Postal Service, Hospitals (only those owned and/or operated by the Federal Government), Military Bases and Tribal Nations. | Downstream | TRC Solutions | All | 2021-07-01 | 43 months | 2022-01-01 | 7,682,759 kWh .672 mW 166,855 Therms | 18360000 | Advice Letter 3815 | 2026-03-31 |  | 55 months | 2026-03-31 | NA
SDG&E | K-12 Schools Energy Efficiency Program (KEEP) | Public Sector- K-12 | SDGE4011 | Resource Acquisition | Public | Public K-12 schools (includes public charter schools) | Downstream | California Retrofit, Inc. (CRI) | All | 2021-07-01 | 40 months | 2022-01-01 | 12,034,838 kWh 1,623 kW 83,447 Therms | 10501926 | Advice Letter 3814 | 2025-12-31 | 2023-12-31 | 40 Months | 2023-12-31 | NA | Advice Letter 4302E
SDG&E | CAP4ZNE | Public Sector- Local Government | SDGE4010 | Resource Acquisition | Public | Local Government - Cities within San Diego and South Orange County, Specialty Districts, Waste and Wastewater facilities | Downstream | Okapi Architecture, Inc. | All | 2022-05-31 | 70 months | 2022-10-01 | 13,887,094 kWh 1,284 kW 176,543 Therms | 9164924 | Advice Letter 4025 | 2028-03-31 | 2024-12-31 | 30 months | 2024-12-31 | N | Advice Letter 4514
SDG&E | Home Energy Audits and Reports Program | Local Behavioral | SDGE4040 | Resource Acquisition | Local | Residential Customers | N/A | Bidgely | All | 2022-10-21 | 53 months | 2023-01-01 | 41,486,876 kWh 899,993 therms 9,188 kW | 15456336 | Advice Letter 4109 | 2027-03-31 |  | 41 months | 2026-03-31 | NA | Advice Letter 4109
SDG&E | Golden State Rebates Program | Statewide Plug Load & Appliance | SDGE_SW_PLA: SW Plug Load and Appliances | Resource Acquisition | Residential | Residential Customers | Midstream/Upstream | CLEAResult Consulting Inc. | All | 2022-01-19 | 39 months | 2022-08-01 | 41,071,725 - kWh 1,206,886 - Therms 5,678 - kW | 43339043 | Advice Letter 3942 | 2025-03-31 |  | 50 Months | 2026-03-31 | N
SDG&E | Residential Energy Solutions (RES) | Residential Single-Family 2.0 | SDGE4001 | Resource Acquisition | Residential | Single-Family Customers | Downstream | Synergy Companies | All | 2022-05-31 | 34 months | 2022-09-01 | 2,509,361 - kWh 233,114 - Therms 2,408 - kW | 5516400 | Advice Letter 4028 | 2025-03-31 |  | 46 Months | 2026-03-31 | N
SDG&E | Ag-STAR (Savings, Training, Assistance, Rebates) Program | Local Agriculture | SDGE4009 | Resource Acquisition | Local | Agricultural Customers | Downstream | Cascade Energy, INC | All | 2022-06-29 | 66 months | 2022-10-28 | 2,400,907 kWh 269,400 Therms 281 kW | 2247714 | Advice Letter 4045 | 2028-03-31 |  | 66 Months | 2028-03-31 | NA
SDG&E | SMART (Savings, Measurement, Assistance, Rebates, Training) Industrials Program | Local Industrial | SDGE4006 | Resource Acquisition | Local | Industrial Customers | Downstream | Cascade Energy, INC | All | 2022-08-31 | 66 months | 2023-01-01 | 38,813,978 kWh 714,051 Therms 3,899 kW | 15950957 | Advice Letter 4079 | 2028-02-29 |  | 65 Months | 2028-02-29 | NA
SDG&E | Quality Residential HVAC Services Program | Statewide Residential HVAC Quality Installation/Quality Maintenance | SDGE_SW_HVAC_QIQM: SW HVAC QI/QM Program | Market Support | Residential | Residential Customers | Quality Contractors work with customers | Frontier Energy, Inc. | All | 2022-11-30 | 52 months | 2023-07-05 | N/A | 27737000 | Advice Letter 4149 | 2027-03-31 |  | 52 Months | 2027-03-31 | NA | Advice Letter 4149
SDG&E | Small Business Savers Program | Small Business Outreach | SDGE4173 | Equity | Commercial | Small Commercial | Downstream/ | Resource Innovations | Demand below 20 kW | 2023-08-29 | 48 months | 2024-01-01 | 550,670 - kWh 157,512 - Therms 50 - kW | 11826502 | Advice Letter 4286 | 2027-12-31 |  | 52 Months | 2027-12-31 | NA | Advice Letter 4286
SDGE | Business Energy Reports (BER) | Non-Residential Behavioral | SDGE4184 | Market Support | Non-Residential | Small Businesses | N/A | Bidgely | Small businesses | 2023-12-21 | 52 months | 2024-04-01 | 41,400,400 - kWh 4,692 - kW | 3538656 | Advice Letter 4354 | 2028-03-31 | Program closing as of 10/31/2025 Closure webinar took place 10/15/2025 Closure request is included in MCAL filing | 51 Months | 2028-03-31 | NA | Advice Letter 4354
SDGE | Learning Energy and Resource Nexus (LEARN) | Workforce Education & Training | SDGE4174 | Market Support | Cross Cutting | Residential and commercial trade contractors, technical workers, architects and engineers, residential customers, commercial customers, agricultural market actors and customers, industrial building owners/managers, facilities staff and tenants | Downstream | RHA | all customer sizes | 2023-11-14 | 42 months | 2024-04-01 | NA | 10835020.38 | Advice Letter 4355 | 2027-12-31 |  | 49 Months | 2027-12-31 | NA | Advice Letter 4355
SDGE | Community Education & Outreach (CEO) Program | Residential Equity Education & Outreach | SDGE4174 | Equity | Residential | Residential and commercial trade contractors, technical workers, architects and engineers, residential customers, commercial customers, agricultural market actors and customers, industrial building owners/managers, facilities staff and tenants | Downstream | GES | all customer sizes | 2024-03-06 | 42 months | 2024-04-01 | NA | 3400000 | Advice Letter 3291 | 2027-12-31 |  | 45 Months | 2027-12-31 |  | Advice Letter 4422
SDGE | Retail, Office, and Wholesale Energy Solutions Program (ROWES) | Retail, Offices and Wholesale | SDGE4170 | Resource Acquisition | Commercial | Retail, office, and wholesale businesses within the commercial sector | Downstream | TRC Solutions | all customer sizes | 2024-08-27 | 55 months | 2025-01-01 | kWh 23,735,006; Therms 1,013,925; kW 1,997 | 15252000 | Advice Letter 4591 | 2029-03-31
SDGE | Grid-Responsive Incentive Design (GRID)- Private Institutions and Healthcare (GRID-PIH) | Private Institutions and Healthcare | SDGE4171 | Resource Acquisition | Commercial | Private Institutions (private schools) and Healthcare businesses within the commercial sector | Downstream | Mendota Group, LLC. | all customer sizes | 2024-12-17 | 53 months | 2025-04-01 | kWh 6,514,604; Therms -325,155; kW 1,034 | 4458930 | Advice Letter 4513 | 2029-05-31
SDGE | Grid-Responsive Incentive Design (GRID)- Lodging (GRID-Lodging) | Lodging: Hotels and Motels | SDGE4168 | Resource Acquisition | Commercial | Lodging (hotel and motel) businesses within the commercial sector | Downstream | Mendota Group, LLC. | all customer sizes | 2024-12-16 | 53 months | 2025-04-01 | kWh 6,299,534; Therms -31,881; kW 1,530 | 4579951.55 | Advice Letter 4594 | 2029-05-31
SDGE | Groceries, Restuarants and Food Storage Program (GRFS) | Groceries, Restuarants and Food Storage Solicitation | SDGE4169 | Resource Acquisition | Commercial | Groceries, restuarants and food storage businesses within the commercial sector | Downstream | AESC | all customer sizes | 2024-11-26 | 52 months | 2025-04-01 | kWh 12,530,672; Therms -9,308; kW 1,572 | 7598748 | Advice Leter 4574 | 2029-03-31
SDG&E | Market Access Program (GRID-MAP) | Market Access Program Solicitation | SDGE4201 - Res SDGE4202 - Com | Resource Acquisition | Residential/Commercial | Residential, Multi-Family and the Commercial Retail, Office and Wholesale sub-segments | Downstream | Mendota Group, LLC. | all customer sizes | 2025-01-31 | 52 months | 2025-07-01 | kWh - 6,696,348 Therms - 33,766 kW - 1,747 | 6000581 | Advice Leter 4621 | 2029-05-31
PG&E | San Mateo County Energy Watch Program | Local Government Partnerships | PGE_Pub_005 | Market Support | Public / Commercial | Public agencies, K-12 public schools, small & hard-to-reach businesses | Downstream | San Mateo City and County Association of Governments | small & medium businesses | 2020-07-01 | 36 months | 2020-07-01 | N/A | 4115250 | No AL Required | 06/31/23 |  | 90 months | 2027-12-31 | 2023-05-19 | 4713-G/6860-E
PG&E | Sonoma Public Energy | Local Government Partnerships | PGE_Pub_008 | Market Support | Public / Commercial | Public facilities, K-12 schools, special districts, municipalities, HTR SMB | Direct contact with municipalities as well as K-12 schools | County of Sonoma | all customer sizes | 2020-07-01 | 36 months | 2020-07-01 | N/A | 3069000 | No AL Required | 06/31/23 |  | 90 months | 2027-12-31 | 2023-05-19 | 4713-G/6860-E
PG&E | Redwood Coast Energy Watch | Local Government Partnerships | PGE_Pub_003 | Market Support | Public / Commercial / Residential / Industrial / Agricultural | Public agencies and HTR customers of all market sectors | Downstream | Redwood Coast Energy Authority | all customer sizes | 2020-07-01 | 36 months | 2020-07-01 | N/A | 4770186 | No AL Required | 06/31/23 |  | 66 months | 2025-12-31 | 2023-05-19 | 4713-G/6860-E
PG&E | Central California Energy Watch | Local Government Partnerships | PGE_Pub_004 | Market Support | Public | Cities, Counties, Special Districts, K-12 school districts | Connecting direct to end use customer based on sector/HTR/DAC qualifiers | San Joaquin Valley Clean Energy Organization | all customer sizes | 2020-07-01 | 36 months | 2020-07-01 | N/A | 5927027 | No AL Required | 06/31/23 |  | 90 months | 2027-12-31 | 2023-05-19 | 4713-G/6860-E
PG&E | Sierra Nevada Energy Watch | Local Government Partnerships | PGE_Pub_007 | Market Support | Public / Commercial | Public sector, unserved SMBs, HTR & DAC | Downstream | Sierra Business Council | all customer sizes | 2020-07-01 | 36 months | 2020-07-01 | N/A | 4309958 | No AL Required | 06/31/23 |  | 90 months | 2027-12-31 | 2023-05-19 | 4713-G/6860-E
PG&E | Central Coast Leaders in Energy Action Program | Local Government Partnerships | PGE_Pub_001 | Market Support | Public | Public agencies including City governments & townships, Tribes, County governments, K-12 public schools, special districts | Outreach to eligible customers through program partners | The Energy Coalition | all customer sizes | 2020-07-01 | 36 months | 2020-07-01 | N/A | 3084000 | No AL Required | 06/31/23 |  | 90 months | 2027-12-31 | 2023-05-19 | 4713-G/6860-E
PG&E | Marin Energy Watch Partnership | Local Government Partnerships | PGE_Pub_002 | Market Support | Public / Commercial | Public sector including the County, cities, towns, school districts and special districts, SMB HTR | Downstream | County of Marin | small & medium businesses | 2020-07-01 | 36 months | 2020-07-01 | N/A | 1401260 | No AL Required | 06/31/23 |  | 90 months | 2027-12-31 | 2023-05-19 | 4713-G/6860-E
PG&E | Energy Access SF | Local Government Partnerships | PGE_Pub_006 | Market Support | Public / Commercial | HTR & DAC in residential and small-medium businesses | Downstream | City and County of San Francisco | small & medium businesses | 2020-07-01 | 36 months | 2020-07-01 | N/A | 2450262 | No AL Required | 06/31/23
PG&E | SW Codes and Standards - Federal C&S | Statewide Codes and Standards | PGE_SW_CSA_Natl | Codes and Standards | N/A | N/A | NonResource | Cohen Ventures, Inc. dba Energy Solutions | N/A | 2020-01-29 | 36 months | N/A | N/A | 4896820 | No AL Required | 2022-12-31
PG&E | SW Codes and Standards - Title 20 C&S | Statewide Codes and Standards | PGE_SW_CSA_Bldg | Codes and Standards | N/A | N/A | NonResource | Cohen Ventures, Inc. dba Energy Solutions | N/A | 2020-02-04 | 36 months | N/A | N/A | 4896820 | No AL Required | 2022-12-31
PG&E | SW Codes and Standards - C&S Coordination | Statewide Codes and Standards | PGE21055 | Codes and Standards | N/A | N/A | NonResource | Cohen Ventures, Inc. dba Energy Solutions | N/A | 2020-03-12 | 36 months | N/A | N/A | 960002 | No AL Required | 2022-12-31
PG&E | SW Codes and Standards -Title 20 C&S | Statewide Codes and Standards | PGE_SW_CSA_Bldg | Codes and Standards | N/A | N/A | NonResource | 2050 Partners | N/A | 2020-02-11 | 36 months | N/A | N/A | 4900077 | No AL Required | 2022-12-31
PG&E | SW Codes and Standards - Federal C&S | Statewide Codes and Standards | PGE_SW_CSA_Natl | Codes and Standards | N/A | N/A | NonResource | 2050 Partners | N/A | 2020-02-11 | 36 months | N/A | N/A | 4899619 | No AL Required | 2022-12-31
PG&E | RAPIDS Wastewater Optimization Program | Local Multi-Sector | PGE_Pub_010 | Resource Acquisition | Public | Public and private sector wastewater treatment and collection systems | Direct Install and Downstream | Alternative Energy Systems Consulting (AESC) | medium and large sized business customers | 2020-10-23 | 24 months | 2022-04-21 | 8,322,571 kWh 1.665 MW 394,200 therms | 4205579 | AL 4284-G/5894-E | 2024-03-31 |  | 57 months | 2026-12-31
PG&E | Industrial Systems Optimization Program (ISOP) | Local Multi-Sector | PGE_Ind_003 | Resource Acquisition | Industrial | Manufacturing and Food Processing market segments including storage and distribution | Downstream | Cascade Energy, INC | small and medium sized business customers | 2020-10-23 | 54 months | 2021-03-01 | 19,139,330 kWh 2.89 MV 1,669,946 therms | 15316931 | AL 4280-G/5890-E | 2025-03-31
PG&E | Business Energy Performance Program | Local Multi-Sector | PGE_Ind_002 | Resource Acquisition | Industrial | Industrial customers in the Petroleum, Chemical and Mineral sub-segments | Downstream industrial program | CLEAResult Consulting Inc. | medium and large sized business customers | 2020-10-23 | 42 months | 2021-03-01 | 38,184,107 kWh 4.72 MW 3,410,143 therms | 22299520 | AL 4279-G/5889-E | 2024-03-31 |  | 46 months | 2024-12-31
PG&E | Grocery Comprehensive Retrofit and Commissioning Program (marketed as "CoolSave") | Local Multi-Sector | PGE_Com_001 | Resource Acquisition | Commercial | Grocery / Supermarket Sector - Retail chains, regional chains and independent operators. | Direct Install and Downstream | kW Engineering, Inc. | all customer sizes | 2020-10-23 | 54 months | 2021-02-01 | 14,768,629 kWh 1.49 MV 0 therms | 5431762 | AL 4281-G/5891-E | 2025-03-31
PG&E | Smart Labs | Local Multi-Sector | PGE_Com_002 | Resource Acquisition | Commercial | Commercial and Higher Education Laboratories | Direct Install and Downstream | kW Engineering, Inc. | all customer sizes | 2020-10-23 | 54 months | 2021-02-01 | 8,379,000 kWh 0.96 MW 404,586 therms | 4378800 | AL 4282-G/5892-E | 2025-03-31
PG&E | Agricultural Energy Savings Action Plan (AESAP) | Local Multi-Sector | PGE_Ag_001 | Resource Acquisition | Agriculture | All Agricultural | Downstream | TRC Solutions | all agricultural end-users | 2020-10-23 | 54 months | 2021-02-01 | 63,258,997 kWh 6.283 MW 205,768 therms | 34254055 | AL 4278-G/5888-E | 2025-03-31
PG&E | Multifamily Energy Savings Program (MESP) | Local Multi-Sector | PGE_Res_003 | Resource Acquisition | Residential | Multifamily | Direct Install and Downstream | TRC Solutions | multifamily with 5+ units | 2020-10-23 | 42 months | 2022-05-21 | 7,721,561 kWh 0.4722 MW 735,451 therms | 11763866 | AL 4285-G/5895-E | 2024-03-31 |  | N/A | N/A | N/A | AL 4754-G/6943-E
PG&E | Government and K-12 Comprehensive Program | Local Multi-Sector | PGE_Pub_009 | Resource Acquisition | Public | Government and K-12 Schools | Direct Install and Downstream | Willdan Energy Solutions | all customer sizes | 2020-10-23 | 54 months | 2022-06-21 | 23,531,801 kWh 3.69 MW 308,997 therms | 9540000 | AL 4283-G/5893-E | 2025-03-31 |  | 102 months | 2029-03-31
PG&E | Advanced Energy Program | Local Multi-Sector | PGE_Com_004 | Resource Acquisition | Commercial | High-tech and BioTech | Downstream | Resource Innovations | All | 2021-05-01 | 53 months | 2022-07-21 | 18,522,333 kWh 3.65 MW 317,741 therms | 13994807 | AL 4362-G/6055-E | 2025-10-01 |  | 95 months | 2029-03-31
PG&E | Healthcare Energy Fitness Initiative | Local Multi-Sector | PGE_Com_005 | Resource Acquisition | Commercial | Healthcare | Downstream | Resource Innovations | All | 2021-05-01 | 53 months | 2021-07-01 | 7,173,637 kWh 1.31 MW 395,937 therms | 11187503 | AL 4363-G/6056-E | 2025-10-01 |  | 95 months | 2029-03-31
PG&E | NetOne | Local Multi-Sector | PGE_Com_003 | Resource Acquisition | Commercial | Broad | Downstream | Ecology Action | All | 2021-01-01 | 60 months | 2021-07-01 | 34,479,519 kWh 3.54 MW 976,395 therms | 32702983 | AL 4364-G/6057-E | 2025-12-31 |  | 108 months | 2029-03-31
PG&E | Non-Residential, Mixed Fuel - California New Construction | Statewide New Construction | PGE_SW_NC_Res_mixed | Market Support | Non-Residential | Commercial, Industrial, Agricultural, High-rise Multifamily, Public | Downstream | Willdan Energy Solutions | All | 2021-04-28 | 55 months *The contract length is through 12/31/25 in compliance with the current approved ABAL. The Intended contract length is 66 months, and the Program service and budget after 12/31/25 shall be contingent upon CPUC approving funding for PG&E's EE program portfolio after 2025. | 2021-08-01 | 55 months: 102,687,122 kWh 27.88 MW 4,664,510 therms Intended 66 months: 122,963,668 kWh 33.38 MW 5,585,561 therms | 55 months: $50,697,244 Intended 66 months: $60,164,150 | AL 4386-G/6094-E | 2025-12-31
PG&E | Non-Residential, All-Electric - California New Construction | Statewide New Construction | PGE_SW_NC_Res_electric | Market Support | Non-Residential | Commercial, Industrial, Agricultural, High-rise Multifamily, Public | Downstream | Willdan Energy Solutions | All | 2021-04-28 | 55 months *The contract length is through 12/31/25 in compliance with the current approved ABAL. The Intended contract length is 66 months, and the Program service and budget after 12/31/25 shall be contingent upon CPUC approving funding for PG&E's EE program portfolio after 2025. | 2021-08-01 | 55 months: 6,977,723 kWh 1.30 MW 4,572,897 therms Intended 66 months: 9,133,221 kWh 1.71 MW 5,985,517 therms | 55 months: $30,714,296 Intended 66 months: $39,796,892 | AL 4387-G/6095-E | 2025-12-31
PG&E | Residential Behavior Program Continuous Energy Feedback Program (CEFP) | Local Multi-Sector | PGE_Res_002d | Resource Acquisition | Residential | All | Downstream | Oracle America Inc. | All | 2021-04-28 | 42 months | 2021-09-01 | 586,900,000 kWh 158 MW 20,912,200 therms | 45770186 | AL 4410-G/6136-E | 2024-11-30 | N/A | 84 months | 2028-06-30 | Y - 7/29/24 | N/A
PG&E | California Energy-Smart Homes Program (CESHP) - All Electric | Statewide New Construction | PGE_SW_NC_NonRes_electric | Market Support | Residential | Single-Family, Multifamily Low-rise, Manufactured Homes, ADUs, Additions/alterations | Downstream | TRC | All | 2021-08-11 | 52 months *The contract length is through 12/31/25 in compliance with the current approved ABAL. The Intended contract length is 67 months, and the Program service and budget after 12/31/25 shall be contingent upon CPUC approving funding for PG&E's EE program portfolio after 2025. | 2022-01-01 | 52 months: 19,136,764 kWh (340.89) MW 1,227,247 therms Intended 67 months: 11,442,883 kWh (571) MW 2,018,728 therms | 39609043 | AL 4465-G/6254-E | 2025-12-31 |  | 60 months | 2026-12-31
PG&E | California Energy-Smart Homes Program (CESHP) - Mixed Fuel | Statewide New Construction | PGE_SW_NC_NonRes_Res_mixed | Market Support | Residential | Single-Family, Multifamily Low-rise, Alterations | Downstream | TRC | All | 2021-09-15 | 52 months *The contract length is through 12/31/25 in compliance with the current approved ABAL. The Intended contract length is 67 months, and the Program service and budget after 12/31/25 shall be contingent upon CPUC approving funding for PG&E's EE program portfolio after 2025. | 2022-01-01 | 52 months: 50,852,787 kWh 60.38 MW 37,245 therms Intended 67 months: 50,869,535 kWh 119 MW 72,211 therms | 52 months: $11,100,009 Intended 67 months: $12,725,453 | AL 4466-G/6255-E | 2025-12-31 | 2023-03-31 | N/A | N/A | N/A | 4680-G_6760-E
PG&E | Statewide State of California Energy Strategy and Support (SOC ESS) | Statewide State of CA | PGE_SW_IP_Gov | Resource Acquisition | Dept. of Corrections | Public | Downstream | AESC | Large | 2021-07-28 | 52 months *The contract length is through 12/31/25 in compliance with the current approved ABAL. The Intended contract length is 72 months, and the Program service and budget after 12/31/25 shall be contingent upon CPUC approving funding for PG&E's EE program portfolio after 2025. | 2021-09-01 | 52 months: 32,601,013 kWh 12.98 MW 557,660 therms Intended 72 months: 49,173,976 kWh 19.60 MW 761,824 therms | 52 months: $18,883,821 Intended 72 months: $25,585,837 | AL 4456-G/6236-E | 2025-12-31 |  | 88 months | 2029-12-31
PG&E | Energize Careers | Statewide WE&T | PGE_SW_WET_Work | Non-Resource | Career and Workforce Readiness | Disadvantaged Workers | Downstream | Strategic Energy Innovations | N/A | 2021-06-25 | 53 months *The contract length is through 12/31/25 in compliance with the current approved ABAL. The Intended contract length is 54 months, and the Program service and budget after 12/31/25 shall be contingent upon CPUC approving funding for PG&E's EE program portfolio after 2025. | 2021-06-25 | N/A | 53 months: $5,962,555 Intended 54 months: $6,010,016 | AL 4442-G / 6207-E | 2025-12-31
PG&E | Energy is Everything (EisE) | Third Party Energy Efficiency Workforce Education and Training Career Connections Program | PGE_SW_WET_CC | Non-Resource | Career and Workforce Readiness | Disadvantaged Workers | Downstream | The Energy Coalition | N/A | 2021-06-25 | 42 | 2021-06-25 | N/A | 3094000 | AL 4443-G / 6208-E | 2025-01-31
PG&E | Simplified Savings Program | Micro And Small Business Equity Program | PGE_Com_SmallBiz | Equity | Equity | Commercial | Downstream | Resource Innovations | Micro / Small | 2022-11-11 | 39 | 2023-01-01 | N/A | 9992829 | AL 4664-G/6734-E | 2025-12-31
PG&E | Commercial Behavioral Program |  | PGE_Com_007 | Resource Acquisition | Commercial | Commercial | Downstream | Oracle
PG&E | Federal Codes and Standards Advocacy | Statewide Codes and Standards Advocacy | PGE_SW_CSA_Natl | Codes and Standards | N/A | N/A | N/A | 2050 Partners | N/A | 2023-10-25 | 26 | 2023-10-25 | N/A | 15189163 | 4801-G / 7029-E | 2025-12-31
PG&E | State Appliance Standards Advocacy Support | Statewide Codes and Standards Advocacy | PGE_SW_CSA_Appl | Codes and Standards | Cross Cutting | N/A | N/A | West Monroe Partners, LLC | N/A | 2023-07-28 | 29 | 2023-07-28 | N/A | 28124000 | No AL Required | 2025-12-31 |  | 65 | 2028-12-31 |  | 5156-G / 7792-E
PG&E | Federal Codes and Standards Advocacy | Statewide Codes and Standards Advocacy | PGE_SW_CSA_Natl | Codes and Standards | N/A | N/A | N/A | Cohen Ventures | N/A | 2023-10-09 | 27 | 2023-10-09 | N/A | 18210000 | 4797-G / 7017-E | 2025-12-31 |  | 64 | 2028-12-31 |  | 5118-G / 7711-E
PG&E | State Appliance Standards Advocacy | Statewide Codes and Standards Advocacy | PGE_SW_CSA_Appl | Codes and Standards | N/A | N/A | N/A | Cohen Ventures | N/A | 2023-10-09 | 27 | 2023-10-09 | N/A | 11610000 | 4797-G / 7017-E | 2025-12-31 |  | 64 | 2028-12-31 |  | 5118-G / 7711-E
PG&E | C&S Program Coordinator & Subprogram Coordinator for State Building Codes Advocacy | Statewide Codes and Standards Advocacy | PGE_SW_CSA_Bldg | Codes and Standards | N/A | N/A | N/A | Cohen Ventures | N/A | 2023-10-09 | 27 | 2023-10-09 | N/A | 5000000 | 4797-G / 7017-E | 2025-12-31
PG&E | State and National Building Codes Advocacy | Statewide Codes and Standards Advocacy | PGE_SW_CSA_Bldg | Codes and Standards | Cross Cutting | N/A | N/A | McHugh Energy | N/A | 2023-05-15 | 31 | 2023-05-15 | N/A | 3309779 | No AL Required | 2025-12-31 |  | 67 | 2028-12-31 |  | 5117-G / 7710-E
PG&E | C&S Compliance Improvement Subprogram - Energy Code Ace - Outreach Support | C&S Compliance Improvement | PGE21053 | Codes and Standards | N/A | N/A | N/A | Cohen Ventures | N/A | 2023-07-24 | 29 | 2023-07-24 | N/A | 1578241 | No AL Required | 2025-12-31 |  | 53 | 2027-12-31 |  | 5118-G / 7711-E
PG&E | C&S Compliance Improvement Subprogram - Energy Code Ace - Tools & Resources Development | C&S Compliance Improvement | PGE21053 | Codes and Standards | N/A | N/A | N/A | Cohen Ventures | N/A | 2023-08-16 | 28 | 2023-08-16 | N/A | 759947 | No AL Required | 2025-12-31 |  | 53 | 2027-12-31 |  | 5118-G / 7711-E
PG&E | C&S Compliance Improvement Subprogram - Energy Code Ace - Subject Matter Expert Support | C&S Compliance Improvement | PGE21053 | Codes and Standards | N/A | N/A | N/A | Cohen Ventures | N/A | 2023-09-01 | 27 | 2023-09-01 | N/A | 2173828 | No AL Required | 2025-12-31 |  | 52 | 2027-12-31 |  | 5118-G / 7711-E
PG&E | C&S Compliance Improvement Subprogram - Energy Code Ace - Subject Matter Expert Support | C&S Compliance Improvement | PGE21053 | Codes and Standards | N/A | N/A | N/A | Gabel Associates | N/A | 2023-08-30 | 28 | 2023-08-30 | N/A | 2911666 | No AL Required | 2025-12-31 |  | 52 | 2027-12-31 |  | 5118-G / 7711-E
PG&E | C&S Compliance Improvement Subprogram - Energy Code Ace - Training Support | C&S Compliance Improvement | PGE21053 | Codes and Standards | N/A | N/A | N/A | Lisa McLain dba. McLain ID Consulting | N/A | 2023-08-30 | 28 | 2023-08-30 | N/A | 5499990 | No AL Required | 2025-12-31 |  | 52 | 2027-12-31 |  | 5118-G / 7711-E
PG&E | C&S Compliance Improvement Subprogram - Energy Code Ace - Subject Matter Expert Support & Tools and Resources Development | C&S Compliance Improvement | PGE21053 | Codes and Standards | N/A | N/A | N/A | NORESCO | N/A | 2023-07-06 | 29 | 2023-07-06 | N/A | 1209782 | No AL Required | 2025-12-31 |  | 54 | 2027-12-31 |  | 5118-G / 7711-E
PG&E | C&S Compliance Improvement Subprogram - Energy Code Ace - Subject Matter Expert Support | C&S Compliance Improvement | PGE21053 | Codes and Standards | N/A | N/A | N/A | Selby Energy | N/A | 2023-09-01 | 27 | 2023-09-01 | N/A | 1422000 | No AL Required | 2025-12-31 |  | 52 | 2027-12-31 |  | 5118-G / 7711-E
PG&E | State Building Codes Advocacy | Statewide Codes and Standards Advocacy | PGE_SW_CSA_Bldg | Codes and Standards | N/A | N/A | N/A | Cohen Ventures | N/A | 2024-05-17 | 55 | 2024-05-17 | N/A | 10196570 | AL 4897-G/7241-E | 2028-12-31
PG&E | State Building Codes Advocacy | Statewide Codes and Standards Advocacy | PGE_SW_CSA_Bldg | Codes and Standards | N/A | N/A | N/A | 2050 Partners | N/A | 2024-05-17 | 55 | 2024-05-17 | N/A | 9500260 | AL 4897-G/7241-E | 2028-12-31
PG&E | State Building Codes Advocacy | Statewide Codes and Standards Advocacy | PGE_SW_CSA_Bldg | Codes and Standards | N/A | N/A | N/A | TRC Solutions | N/A | 2024-05-17 | 55 | 2024-05-17 | N/A | 6996036 | AL 4897-G/7241-E | 2028-12-31
PG&E | State Building Codes Advocacy | Statewide Codes and Standards Advocacy | PGE_SW_CSA_Bldg | Codes and Standards | N/A | N/A | N/A | Frontier Energy, Inc. | N/A | 2024-05-17 | 55 | 2024-05-17 | N/A | 3378000 | AL 4897-G/7241-E | 2028-12-31
PG&E | Codes and Standards Code Readiness | Codes and Standards Code Readiness | PGE21056 | Codes and Standards | N/A | N/A | N/A | 2050 Partners | N/A | 2024-06-06 | 66 | 2024-06-06 | N/A | 34700000 | AL 4908-G/7259-E | 2029-12-31
PG&E | Measured Savings Program for Summer Reliability (MSPSR) | Summer Reliability Platform Administrator | PGE_Com_006 | Resource Acquisition | Commercial, Residential | All | Downstream | AESC, Inc | Medium and large sized customers | 2024-07-02 | 48 | Com: 8/4/2024 Res: 11/4/2024 |  | 30000000 | 4927-G / 7304-E | 2028-07-02
PG&E | Powerful Neighborhoods | Zonal Equity Electrification Program (ZEEP) | PGE_Res_004a | Equity | Res, Com, Ag, Pub | N/A | Downstream | Resource Innovations | Highly targeted geographically | 2024-10-01 | 37 | 2025-03-01 | N/A | 6183708 | 4941-G / 7325-E | 2027-11-01
PG&E | Electrify My Block (EMB) / Sustainable Energy Home Improvement Program (SEHI) | Zonal Equity Electrification Program (ZEEP) | PGE_Res_004b | Equity | Residential, Commercial | N/A | Downstream | Quest | Highly targeted geographically | 2024-12-01 | 37 | 2025-03-01 | N/A | 5609545 | 4963-G / 7360-E | 2027-12-31
PG&E | Empower My Home Pilot (EPMH) | Residential Equity | PGE_Res_005 | Equity | Residential | Residential customers in assigned PUMAs, up to 400% FPL | Downstream | Resource Innovations | Highly targeted geographically | 2024-11-01 | 37 | 2025-03-01 | N/A | 8983134 | 4954-G / 7348-E | 2027-11-30
PG&E | Residential Clean Energy Orchestration (CEO) | Res CEO | PGE_Res_006 | Market Support | Residential |  | Downstream | TRC |  | 2025-04-01 | 37 | 2026-01-01 |  | 5700000 | 5031-G / 7503-E | 2028-04-30
PG&E | Commercial Strategic Energy Management (C SEM) | Commercial SEM | PGE_Com_009 | Resource Acquisition | Commercial | Commercial, Institutional, and Public segments including, but not limited to, higher education, K-12 schools, Government, hospital, lodging, office, grocery, commercial multifamily, warehouse, and other healthcare. | Downstream | Stillwater Energy, Inc. | All | 2024-12-15 | 85 | 2025-03-01 |  | 14996501 | AL 5013-G/7461-E | 2031-12-31