## Sheet1
MTWG Pat 2 Workplan
Draft for 8/11 WG Mtg.
| August | September | October | November | January | February
| Meeting #1: 8/11 | Meeting #2: TBD | Meeting #3: TBD | Meeting #4: TBD | Meeting #5: TBD | Meeting #6: TBD
1) Savings Attribution | Education/ Option Exploration | Develop Approach(es) | Refine Approach(es) | Finalize Approach(es)
2) Goal Setting | Education/ Option Exploration | Develop Approach(es) | Refine Approach(es) | Finalize Approach(es)
3) MTI Cost-Effectiveness Framework | October: Review MTWG's Original Proposed Approach and Consider Improvements*; November: Refine/Finalize Proposed Improvements
4) Minimizing Duplication/Negative Overlap MTIs & Other EE Efforts | October: Review MTWG's Original Proposed Approach and Consider Improvements**; November: Refine/Finalize Proposed Improvements
5) Report to Commission | January: Review Draft Report Language/ Recommendations; February: Finalize Report Language/ Recommendations
* Consideration should be in light of where MTWG is heading on Savings Attribution (and Goal Setting), plus any related Commission decisions/directives
on cost-effectiveness issues since MTWG Part 1.
**This should also be in light of where MTWG is heading on Savings Attribution (and Goal Setting), and should also attempt to flesh out further from MTWG Part 1
a multi-pronged approach to different types of potential program overlaps (e.g., MTIs w/RAs; MTIs w/other MTIs; etc.)