## Slide 1
Concept Development
Program Development
Market Deployment
Phase I
Phase II
Phase III
Concept Scanning & Identification
Concept Development & Assessment
Stage 1
Stage 2
  Scanning, identification, & collection of MT ideas
  MT intake & ideation
  Use available, structured data into prioritization model
  Abstract of barriers, opportunity & program development
  Develop initial logic model
Strategy Development
Strategy Testing
  Baseline data collection & identification
  Market & product assessment (leverage points)
  Early EM&V and Portfolio Coordination Plan is developed
  Market test & strategies performed
  MT Accord development initiated (Tier II AL)
  Commitment to market
  Refine logic models
  Long Term market indicators development
Market Development
Long Term Monitoring
  Full(er) scale MT deployment
  Periodic review of market interventions to identify re-tooling
  MTI monitored for long term benefits vs. costs
  Long term market progress indicators tracked
  Refine coordination plans with rolling portfolio
Stage 3
Stage 4
Stage 5
Stage 6
Transition or Sunset MTI
  MT incentives/interventions concluded and/or transitioned to:
  A.)Codes & Standards
  B.) EM&V for long term monitoring
  C.)Program team for MT relaunch
Stage 7
Working Group Final Revision 1/4/19
Level 1 Funding (Source TBD)
Level 2 Funding (MT B/A)
Activities
Review 1: Review collected info on the concept development phase and provide a recommendation on 3-5 MTIs to proceed and authorize funding for the execution of the MTI Development Plan
Review 2: Review the draft Market Transformation Accord and provide a recommendation on whether the MTI is worth scaling up to Phase III, Market Deployment.
Deliverables
1) Disposition report on all MT concept submissions
2) Rank-ordered list of submissions, based on MT PA SMEs’ high-level review of MT Initiatives (MTIs)
1) List of MT concepts
ranked on the general
MT criteria, validated with
currently available data
2) Preliminary development plans for data/research needed to conduct due diligence on each MT concept, including budgets and timelines
3) After stakeholder review, the top MT concept development plans can be included in a draft the MT Development Plan Advice Letter.
1) Market characterization studies, including
  • baselines
  • leverage points
  • market potential (high level)
  • market progress
  indicators
2) Workpapers and/or technology assessment reports
3) Pilot testing plans, including pilot evaluation plans
4) Portfolio fit risk assessment (projections of savings potential, savings likelihood, and impact on EE portfolio goals)
Review
1
1) Completed pilot test reports, or other MT concept due diligence reports
2) Rank ordered list of MT Accord candidates, including reports on how well they meet the general MT criteria:
Note: Criteria for each MTI will be unique to the MTI. Stage 5 & Stage 6 will likely run in parallel.
Periodic report out of MTI deployment progress
Criteria and market progress indicators will be unique to each MTI. All MTI-specific criteria and market indicators will be laid out in the MT Accord.
1) A successfully transitioned or exited MTI.
2) Report on savings achieved, lessons learned
Review
2
Review
3
Level 3 Funding (MT B/A)
Review 3: Periodically review of the long-term progress indicators and decide whether further action is needed on the MTI before transitioning or sun setting.
Decision

## Slide 2
Concept Development
Program Development
Market Deployment
Phase I
Phase II
Phase III
Concept Scanning & Identification
Concept Development & Assessment
Stage 1
Stage 2
  Rank ordering of ideas based on maturity and pre-existing documentation:
  Level 1 - Pre-screening
  Level 2 - Proposed idea and category
  Level 3 - Products benefits, costs, distribution
  Level 4 – MT intervention logic
  Level 5 – Turnkey MT quantitative documentation
  To advance (i.e., be included in a MT Development Plan), the MT concept must be one of the top ideas, after considering the general MTI Criteria. (weighting to be determined later).
Strategy Development
Strategy Testing
  To advance (i.e., be considered for pilot testing or other strategy testing) the MT concept must be one of the top ideas, after considering the general MTI Criteria. (weighting to be determined later).
  -Clearly understood market leverage points
  -Measure savings
  -Program Portfolio fit
  To advance and be considered for inclusion in an MT accord, an MTI must meet its own defined pilot success criteria and continue to rank highly on the General MTI Criteria.
  Strategy testing should focus on primarily testing the intervention strategy, the ability to engage contributing non-MTPA market actors, and portfolio fit.
Market Development
Long Term Monitoring
  Criteria for each MTI will be unique to the MTI (see Stage 6). Stage 5 & Stage 6 will likely run in parallel.
  - Exit/transition criteria and market progress indicators will be unique to each MTI. All MTI-specific criteria and market indicators will be laid out in the MT Accord.
  - The prime objective of monitoring the General MTI Criteria will be monitored to identify changes that may affect forecasted savings potential
Stage 3
Stage 4
Stage 5
Stage 6
Transition or Sunset MTI
  Due to the unique nature of each MTI, the MTI-specific exit criteria will be laid out in the MT Accord. The overarching exit criteria would be:
  “When the annual forecast of MTI savings shows that continued scaling would not result in a cost-effective program.” Or, “When a better (lower cost, more effective) intervention can be implemented.”
Stage 7
Criteria and Data Needs
Level 1 Funding (Source TBD)
Level 2 Funding (MT B/A)
Criteria
Review 1: Review collected info on the concept development phase and provide a recommendation on 3-5 MTIs to proceed and authorize funding for the execution of the MTI Development Plan
Review 2: Review the draft Market Transformation Accord and provide a recommendation on whether the MTI is worth scaling up to Phase III, Market Deployment.
Data Needs
As submitted on the Application Form, and reviewed by technologists and subject matter experts in engineering)
- Existing internal research-workpapers, EM&V reports
- Secondary research – industry market reports
- Others?
  - Existing internal research-workpapers, EM&V reports
  -Secondary research – industry market reports
  - Primary research – Commissioned industry market reports, market characterization studies, market leverage point and/or market barrier studies
  - Others?
Review
1
- Existing internal research-workpapers, EM&V reports
- Secondary research – industry market reports
- Primary research – Commissioned industry market reports, market characterization studies, market leverage point and/or market barrier studies
  See stage 6.
- Existing internal research-workpapers, EM&V reports
- Secondary research – industry market reports
- Primary research – Periodic industry market reports, market characterization studies, market leverage point and/or market barrier studies
- Existing internal research-workpapers, EM&V reports
- Secondary research – industry market reports
- Primary research – Periodic industry market reports, market characterization studies, market leverage point and/or market barrier studies
Review
2
Review
3
Level 3 Funding (MT B/A)
Review 3: Periodically review of the long-term progress indicators and decide whether further action is needed on the MTI before transitioning or sun setting.
Decision

## Slide 3: General MT criteria categories for weighting
Projected long term cost effectiveness (including energy savings potential and total cost of the MTI)
Feasibility
  Technical performance of the measure/solution
  Market leverage point(s) / MTI logic (including supply chain readiness)
  Measurability/evaluability
  Agreement of non-MT PA market actors
  Likelihood of Persistence (longevity of MTI relevance)
Portfolio Fit (Coordination with portfolio)
Societal Benefits
  Policy fit
  Equity
  Non-energy benefits (including workforce development)
  From the customer perspective, is there a compelling value proposition?

## Slide 4
Concept Development
Program Development
Market Deployment
3P RFA
Decision
Phase I
Phase II
Phase III
Concept Scanning & Identification
Concept Development & Assessment
Stage 1
Stage 2
  Scanning, identification, & collection of MT ideas
  MT intake & ideation
  Use available, structured data into prioritization model
  Abstract of barriers, opportunity & program development
  Develop initial logic model
Strategy Development
Strategy Testing
  Baseline data collection & identification
  Market & product assessment (leverage points)
  Early EM&V and Portfolio Coordination Plan is developed
  Market test & strategies performed
  MT Accord development initiated (Tier II AL)
  Commitment to market
  Refine logic models
Market Development
Long Term Monitoring
  Full(er) scale MT deployment
  Long Term market indicators development
  MTI monitored for long term benefits vs. costs
  Long term market progress indicators tracked
  Refine coordination plans with rolling portfolio
Stage 3
Stage 4
Stage 5
Stage 6
Transition or Sunset MTI
  MT incentives/interventions concluded and/or transitioned to:
  A.)Codes & Standards
  B.) EM&V for long term monitoring
  C.)Program team for MT relaunch
Stage 7
Decision
Decision
Working Group Revision 12/31/18

## Slide 5: Key Decision Points Added to Stage Gates
  D1. (Between Stages 2 & 3): Decision (approval) to spend money on a handful of initiatives to fully develop them (ramp up exploration)
  D2. (Between Stages 4 & 5): Decision (approval) to fully implement MTI/Accord (approve full scale implementation)
  D3. (Between Stages 6 & 7): Adjust or exit, or continue as designed
  Other Stages: Interim smaller decision points (A, B, C, D) but important internal gates throughout, e.g., off-ramps in Stage 4
Notes: Margie Gardner slide

## Slide 6
Stage 1
Stage 2
Stage 3
Stage 4
Stage 5
Concept Development
Program Development
Market Intervention
Concept Intake & Selection
Strategy Development
Strategy Testing
Market Development
Transition & Monitoring
Stage 0
Logic Development
MTI1
Baseline data collection, forecasting,
PAs develop MT Plan laying out scope, schedule, KPIs, budget estimate for 10 year cycle; 1-2-year workplan with detail budget for stage 4
Early pilot testing. Iterate.
Develop MT Accord with clear metrics, market engagement/commitment (manufacturer, distributor, rep, trade allies, etc. support for MTI), RA integration plan, etc.
PAs file Tier I/II Als for pilot approval. Large-scale and long-term commitment made.
Full Scale Market Development (data infrastructure, 3P spec engagement, supply chain and workforce development, RA, ME&O, etc.
Report out; auto-continue if progressing as expected
Ongoing Monitoring, Assessment, and integration
Transition to C&S
Market transition Strategy
MTI3
MTI4
MTI6
MTI7
MTI1
MTI2
MTI4
MTi3
MTi5
MTi6
MTI1
MTI1
MTI4
MTI3
MTI1
MTI3
MTI1
C&S & Market Transition
MTI subject to additional scrutiny and may drop out due to missing key milestones
Market/Program Scale up
Monitoring/Scale Down/Transition
MT Optimization Model auto-ranks submissions based on quantitative data
SME’s review and validate qualitative aspects & data sources
Execute Contracts W/ 3P
Stakeholder-informed prioritization framework (process, Optimization Model, source data, etc.)… created through consensus process.
Transparent criteria send clear signal to MT ecosystem.
Initial budget provided by PUC
Idea intake includes: (1) structured data feeds into prioritization model, resulting in automated ranking based on quantitative data; (2) Abstract of barrier, opportunities, and program development; (3) Supporting documents for structured data inputs
PAs/PRG/CAEECC review and validate submissions, resulting in ‘near automated’ filtering and advancement of ideas, as well as a ranked backlog
PUC Approval / Rejection
Intake Form
C&S Program
ET Program
Third-Parties
M1
M0
M3
M4
M5
Mn
3P RFA
Idea Backlog
M2
=policy stakeholders engaged
Notes: Brian Barnacle revised slide

## Slide 7
Stage 1
Stage 2
Stage 3
Stage 4
Stage 5
Stage 6
Stage 7
Phase 1: Concept Development
Phase 2: Program Development
Phase 3: Market Deployment
Concept Scanning & Identification**
  Identification, collection and scanning of MT Concept Development Plan candidates
  Initial assessment of market dynamics, available data and intervention strategies
  MT PAs coordinate with ETP, 3Ps, C&S, & RA programs to prioritize market opportunities
Concept Development & Assessment**
  MT PAs characterize the target market
  Identify market barriers/failures for MT to address
  Identify market opportunities
  Based on market characterizations, prioritize concepts for further assessment
Market Baselines & Forecasting
  Identify data needs and sources of data including proprietary data, NDAs
  Identify ways to embed EM&V into pilot
  Develop initial baseline strategy
  Consider incorporating CPUC indicators of “potentially promising” programs
Strategy Testing & Finalization
(Market Tests)
  PAs coordinate with/solicit input from 3Ps to design market intervention strategies. Where needed coordinate with RA programs
  PAs develop budget, initial logic models, pilot milestones, and file to launch market tests
  Market tests may be locationally specific
Market
Development
  MT PAs refine initiative plans from market tests for full-scale MT Accords
  Full scale MTI: MT PAs establish baselines, refined logic models, and milestones
  CalTF baseline input
  MT PAs present promising MT Accords via MTAB
  MT PAs file Tier II AL. or include MT Accord in ABAL
Long Term Monitoring
  MT PAs & MT Advisory Board monitor interim and long-term indicators of market effects
Transition or Sunset MTI
  MT PAs implement exit strategy or transition strategy
  MTI transitioned to Codes & Standards, RA program and/or other regulatory policies.
  May require other interventions to assist w/ C&S adoption, deployment, and enforcement
Key Activities
Key Outputs
  Roadmap of identified Market Transformation opportunities
  MT opportunities may be prioritized/ grouped by intervention type, sector
  Narrowed list of MT Initiatives (MTIs)
  Initial identification of MT intervention strategy/approach
  Initial logic models and intervention theory
  Data Collection and Analysis Plan
  Clearly defined market, barriers to address, intervention strategy, baseline & milestones and EM&V plan
  Market testing: MT PAs establish criteria for judging whether a market test is successful and worthy of scaling up.
  MT Accord(s)
  Early EM&V plan and key MT metrics for market tests and full scale MTIs
  MT Accord(s)
  Measurable market-effects and performance indicators
  Deemable elements of MTIs sent to RA programs?
  Market readiness for code adoption
Policy Prioritization & Initial Budgeting**
  Market Transformation Advisory Board (MTAB) guides direction for:
    Policy focus for MT
    Initial budget funding through Stage 4
  Explore possibility of limited CPUC delegation of authority for decision making with appealable outcomes to CPUC.
  Strategic direction for pursuing MT Initiatives to establish initial screening and solicitation criteria
  Guidance to outline initial MT funding levels before solicitation of MTIs
Process
0. MT Ideas Submitted via Ideation Process
2b. MTI Reviewed by MTAB then CPUC
2a. MT PAs Develop
3-5 MT Initiatives (MTIs)
3. MT PAs file Tier I/II ALs for MT Market Tests
4. MT PAs implement MT Pilots
5. MT PAs develop MT Accords and file w/ CPUC
MT Intake form
1. MT Ideas Shared at MTAB
6. Ongoing Monitoring of MTIs via MT PAs and MTAB
Key Questions
7. Transition
Or Cancelation of MTI
CAEECC Market Transformation Working Group Revised Stage Gate Process
  Note: Edits shown in red text
D1
D2
D3
**Use publicly available, existing data for Stages 0-2 then proprietary data under Non-Disclosure Agreements (NDAs) for subsequent stages, MTIs should be winnowed down during stage gates
What are good policy applications for MT?
Why are they good candidates for further MT Development and Research? How good?
What do the Development Plan results tell us about these MTI candidates?
Why are they good candidates for further MT Development and Research?
Which MT approaches can gain traction with customers and industry partners, and can impact markets?
How do we scale successful MT initiatives into working MT program approaches?
Are the MT initiatives achieving planned goals? When should MTIs be included in Rolling Portfolio?
Has the MTI succeeded or failed? Are market dynamics self-sustainable? Has the MTI created opportunities better served through C&S, RA programs or other reg polices?
Tech Sub-Committee
Technical Sub-Committee
MT Advisory Board
MT Advisory Board
MT Advisory Board
Tech Sub-Committee
Concept Advancement
MT Advisory Board
MT Advisory Board (MTAB) Establishes Policy Direction
Notes: Talking Points:
Presented IOU initially proposed stage gate process and made some modifications which I will explain shortly
[Transition to high-level visual slide]
[Discuss from top to bottom and pause at the end of each phase]
Added stage gate 0, and modified stage gate 7 to reflect a couple of outcomes with MT: exiting MT intervention in addition to transition to C&S
Added process flow map at bottom to explain stages of key developments and decision-,aking
[Start at Stage Gate 0 and continue onward]

## Slide 8: SCE Thoughts on MT Governance Model
Market Transformation Advisory Board (MT AB)
Technical Sub-Committee (aka Initiative Review Committee)
Market Transformation Program Administrators (MT PAs)
MT SME
IOU SME
EJ SME
3P SME
Ratepayer SME
Industry SME
Labor SME
MT SME
IOU SME
MT SME
EM&V SME
ED Staff
IOU SME
ED Staff
MTI 1
MTI 4
MTI 2
MTI 3
MTI 5
MT Policy Guidance
MT Administration
MT Technical Guidance
3P
3P
3P
3P
3P
MT Implementation
MT Role
What should we use MT for?
(MT Policy Objectives)
What MT tactics should be employed?
(MT Targets and Design)
How should MT be applied?
(MT Methods)
How do we achieve MT targets?
(MT Tactics)
MT Focus Areas
MT IE