## Slide 1: High-level Summary of CAEECC Interview Findings
Facilitator: Dr. Jonathan Raab, Raab Associates
2018 Coordinating Committee - Launch Meeting - #15
February 15, 2018 10a-5p
NRDC, 111 Sutter St, San Francisco

## Slide 2: Chronology
2007
CPUC adopts Big Bold Energy Efficiency Strategies
2008
CPUC adopts Strategic Plan to achieve “all cost-effective energy efficiency”
Multiple dates
2015
2016
Multiple stakeholder groups promoted including EE Peer Review Groups and Program Advisory Groups
2017
13 CAEECC meetings held and multiple sub-committees
2018
Redefine roles of the CAEECC
6 Ad Hoc meetings and 1 CC meeting
Decision 15-10-028 establishes CAEECC
August 16 3rd Party Decision (at least 60% designed/implemented by 2020)
PA Business Plans filed

## Slide 3: Overview
Accomplishments
Challenges and Limitations
Meetings and Decision-Making

## Slide 4: Accomplishments
Most CC Members viewed CAEECC as primarily successful in a) convening diverse parties and b) fostering information sharing.
Specifically CAEECC:
Helped illuminate a wide range of energy efficiency related issues “really valuable to talk about important issues,” and in turn created “greater understanding of the perspectives of the different sectors represented.”
Created valuable two-way communication flow between the PAs and non-PAs (and to a lesser degree, with the CPUC)
Set a tone that was “transparent, frank and open”, leading to “some notable increased cooperation” and “important relationships were developed” among stakeholders.

## Slide 5: Accomplishments
Many PAs and non-PAs felt that the CAEECC discussions helped to inform the PA’s Business Plans (“often tedious but really helped to improve our filing”), while some saw little evidence of that.

## Slide 6: Accomplishments
Although there was little, if any, formal consensus or agreement reached on recommendations and advice, many felt that the CAEECC, “created a space to be collaborative,” and that the discussions helped spin off significant collaborations among CAEECC Members, including successful joint-filings before the CPUC (e.g., for an Independent Evaluator).

## Slide 7: Accomplishments
Many said that the CAEECC helped inform and sharpen individual member filings and positions on ongoing EE issues before the CPUC, though some lamented that the CAEECC didn’t seem to reduce the number of litigated issues or data requests before the CPUC.

## Slide 8: Challenges and Limitations
Members viewed the overall timeline for developing Business Plans as too aggressive, and even unrealistic, and very challenging for CAEECC.
As filing deadlines approached, the need to produce and review multiple sets and iterations of material was difficult for PAs and non-PA Members alike

## Slide 9: Challenges and Limitations
Regarding the CAEECC’s input into the Business Plan process:
Many non-PAs were frustrated that their advice was not integrated into the PA’s Business Plans
Some PAs felt that they did not get sufficiently cohesive and timely advice from the CAEECC, especially on the draft Business Plan iterations

## Slide 10: Challenges and Limitations
Regarding the CAEECC’s interface with the CPUC:
Lack of clear and timely decisions on energy efficiency matters by the CPUC was often challenging for CAEECC
CPUC’s rotating staff participation and “hands-off” approach at the CAEECC meetings was frustrating to numerous Members who would like to see more active CPUC engagement. As one Member put it, “Energy Division’s interest in the CAEECC seems to wax and wane.”

## Slide 11: Challenges and Limitations
Regarding the CAEECC’s scope going-forward:
The CPUC’s 3rd party decision (August 2016) is presenting ongoing challenges and confusion for the CAEECC in terms of what topics it should and should not discuss and how it conducts meetings (e.g., Conflict of Interest Guidelines). Some illustrative quotes:
“This precludes the CAEECC from being able to vet implementation plans and shifted the overall CAEECC purpose--perhaps to more of a policy orientation”
“Adding insurmountable conflict of having implementers and PAs working together on implementation and program designs—is very unfortunate”
“Still also have Annual Advice Letters (on budget); reporting on implementation progress and overall strategy refinements down the road; and anything else the CPUC directs the CAEECC to undertake”
“CPUC will need to help sort out role of CAEECC going forward vs. other groups such as the new Procuremnt Review Groups

## Slide 12: Meetings
Meetings were not as efficient and effective as they should have been:
Agendas often had too many topics and unrealistic timeframes, and the agenda-setting process itself was often opaque
Meeting materials were often posted late, leaving insufficient time for Members to adequately prepare, and, “proposals were often not documented in writing ahead of meetings”
Members often didn’t adequately review posted material to come prepared to fully participate
Some Members regularly wandered off topic (“dragging things off the wheels”), or dominated the discussions
The timeframes for agenda topics were often exceeded, and strategies for working through particular agenda items were frequently not clearly articulated

## Slide 13: Decision-Making
Despite robust discussions, finding consensus on recommendations/advice was extremely rare:
Many expressed their frustration with the lack of consensus, “If the CAEECC had come to consensus on more issues it would have more influence with the PAs and at the CPUC”
The sheer volume of issues, tasks, and material made it very difficult to dedicate the time needed to seek agreement
Some participants were highly resistant to modifying initial or seemingly fixed positions, and often Members “just weren’t on the same page”
The facilitators generally did a decent job running the meetings, but were not very effective in helping Members reach agreements
  Many Members pointed out, that even without reaching consensus, it would still have been very helpful to seek convergences, narrow differences, and better document two or more options

## Slide 14: CAEECC Quarterly Meeting Dates
February 15
May 10 (Other May Options--1,3, or 8)
August 2 (Other Options—August 7 or 9; or 9/13 but too late for input to Advice Letter)
December 6 (Other December Options—4)